## Dashboard
ESP32-S3 Solo Program Dashboard
Project Start | 2026-07-13 |  | Reporting Week | 1 |  | Production Release Week | 78
Planned Completion | 1.09% |  | Actual Completion | 17.11% |  | Schedule Variance | 16.02%
Late Tasks | 0 |  | Completed Tasks | 22 |  | Total Work Packages | 133
Cluster | Name | Start | End | Planned % | Actual % | Variance | Tasks | Complete | Late | Gate
A | Product Definition and Planning | 1 | 6 | 13.16% | 100% | 86.84% | 10 | 10 | 0 | G-A
B | Engineering Foundation | 7 | 12 | 0% | 100% | 100% | 12 | 12 | 0 | G-B
C | Platform and Architecture Development | 13 | 34 | 0% | 0% | 0% | 32 | 0 | 0 | G-C
D | Product Feature Development | 35 | 56 | 0% | 0% | 0% | 33 | 0 | 0 | G-D
E | Verification and Qualification | 57 | 70 | 0% | 0% | 0% | 20 | 0 | 0 | G-E
F | Industrialization and Production Release | 71 | 78 | 0% | 0% | 0% | 12 | 0 | 0 | G-F
G | Field Operation and Lifecycle Maintenance | 79 | 90 | 0% | 0% | 0% | 14 | 0 | 0 | G-G
Current Gate Logic and Assumptions
One owner means every row is assigned to “Me”. Overlapping rows are intended to be interleaved within the same week.
Task Actual Completion starts at 0% because no execution evidence was provided. Enter evidence-based progress only.
A cluster gate is accepted only when its gate row reaches 100% and the stated completion criteria are met.
Week 78 is the production release baseline. Weeks 79–90 cover staged rollout, stabilization, upgrades, hardware support and closure readiness.

## Control
ESP32-S3 Solo Project WBS — Control
Field | Value | Purpose | Editable?
Project Name | ESP32-S3 Production Firmware Program | Program tracked by this workbook | Yes
Owner | Parthasarathy CP | Single accountable owner for every work package | Yes
Project Start | 2026-07-13 | Monday used to derive weekly dates | Yes
Reporting Week | 1 | Update this value from 1 to 90 for planned-progress/status calculations | Yes
Production Release Week | 78 | Cluster F production release baseline | No
Lifecycle Baseline End Week | 90 | Initial field stabilization and lifecycle closure horizon | No
Overall Planned Completion | 1.09% | Weighted planned progress at Reporting Week | Formula
Overall Actual Completion | 17.11% | Weighted sum of task Actual Completion values | Formula
Schedule Variance | 16.02% | Actual minus planned | Formula
Late Tasks | 0 | Zero-progress tasks whose end week is before Reporting Week | Formula
Completed Tasks | 22 | Tasks at 100% | Formula
Total Work Packages | 133 | Detailed WBS rows | Formula
Progress Update Method
1 | Set Reporting Week in B7.
2 | Update WBS column Q (Actual Completion %) using the dropdown.
3 | Store links or file paths to evidence in WBS column X (Notes).
4 | Review Dashboard variances, late tasks and cluster gates.

## WBS
ESP32-S3 Production Firmware Program — Detailed Work Breakdown Structure
Baseline: 90 weeks, one owner. Update Actual Completion % and evidence links; all other progress fields calculate automatically.
WBS ID | Cluster | Cluster Name | Phase | Phase Name | Weekly Activity / Work Package | Dependencies | Start Week | End Week | Duration (wks) | Effort Points | Owner | Evidence / Deliverable | Completion Criteria | Gate | Planned Progress % | Actual Completion % | Weight % | Planned Contribution % | Actual Contribution % | Status | Planned Start | Planned Finish | Notes / Evidence Link
A1.1 | A | Product Definition and Planning | A1 | Product concept definition | Define users, operating environment, installation, power, connectivity, UI, maintenance and update strategy |  | 1 | 1 | 1 | 1 | Me | Product concept document and primary use-case list | All primary users, operating modes and maintenance assumptions documented |  | 100% | 100% | 0.545% | 0.545% | 0.545% | Complete | 2026-07-13 | 2026-07-19
A1.2 | A | Product Definition and Planning | A1 | Product concept definition | Model normal and abnormal operating scenarios | A1.1 | 1 | 2 | 2 | 2 | Me | Normal/abnormal scenario catalogue | Every expected device mode and principal failure scenario has defined behavior |  | 50% | 100% | 1.09% | 0.545% | 1.09% | Complete | 2026-07-13 | 2026-07-26
A1.3 | A | Product Definition and Planning | A1 | Product concept definition | Define firmware, cloud, mobile, factory and recovery boundaries | A1.1 | 2 | 2 | 1 | 1 | Me | System context diagram and product-boundary document | Responsibilities are separated with no ambiguous ownership |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-07-20 | 2026-07-26
A2.1 | A | Product Definition and Planning | A2 | Requirements engineering | Write uniquely identified functional requirements | A1.2,A1.3 | 2 | 3 | 2 | 2 | Me | System requirements specification with FR identifiers | Each function is measurable and traceable |  | 0% | 100% | 1.09% | 0% | 1.09% | Complete | 2026-07-20 | 2026-08-02
A2.2 | A | Product Definition and Planning | A2 | Requirements engineering | Set measurable non-functional budgets for timing, memory, power, availability and security | A2.1 | 3 | 3 | 1 | 1 | Me | Non-functional requirements specification | Every NFR has a numeric target and test method |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-07-27 | 2026-08-02
A2.3 | A | Product Definition and Planning | A2 | Requirements engineering | Define hardware, communications, diagnostics, manufacturing and OTA interfaces plus environmental constraints | A2.1 | 3 | 4 | 2 | 2 | Me | Interface control document and environmental/regulatory checklist | All external and internal interfaces have limits, ownership and error behavior |  | 0% | 100% | 1.09% | 0% | 1.09% | Complete | 2026-07-27 | 2026-08-09
A2.4 | A | Product Definition and Planning | A2 | Requirements engineering | Build requirements traceability matrix and initial acceptance-test list | A2.2,A2.3 | 4 | 4 | 1 | 1 | Me | Requirements traceability matrix and acceptance-test catalogue | Every requirement maps to architecture and a verification method |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-08-03 | 2026-08-09
A3.1 | A | Product Definition and Planning | A3 | Feasibility and risk analysis | Validate ESP32-S3/Heltec V3 hardware constraints, pins, flash, PSRAM, RF, USB and power controls | A2.3 | 4 | 5 | 2 | 2 | Me | Hardware feasibility report and verified pin/constraint list | Board revision and all critical electrical constraints are confirmed |  | 0% | 100% | 1.09% | 0% | 1.09% | Complete | 2026-08-03 | 2026-08-16
A3.2 | A | Product Definition and Planning | A3 | Feasibility and risk analysis | Prototype high-risk software capabilities: provisioning, LoRaWAN, TLS, OTA, sleep and storage recovery | A3.1 | 5 | 6 | 2 | 2 | Me | Proof-of-concept applications and test logs | Each high-risk assumption is demonstrated on target hardware |  | 0% | 100% | 1.09% | 0% | 1.09% | Complete | 2026-08-10 | 2026-08-23
A3.3 | A | Product Definition and Planning | A3 | Feasibility and risk analysis | Create risk register and preliminary threat model; close Cluster A gate | A2.4,A3.2 | 6 | 6 | 1 | 1.2 | Me | Risk register, threat model and requirements-baseline review record | Risks have mitigations and the requirements baseline is accepted | G-A | 0% | 100% | 0.654% | 0% | 0.654% | Complete | 2026-08-17 | 2026-08-23
B1.1 | B | Engineering Foundation | B1 | Development environment setup | Install and pin VS Code, ESP-IDF, Git, Python, CMake/Ninja, drivers and debugger support | A3.3 | 7 | 7 | 1 | 1 | Me | Tool-version manifest and installation record | Pinned tools execute successfully on the Windows workstation |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-08-24 | 2026-08-30
B1.2 | B | Engineering Foundation | B1 | Development environment setup | Build, flash and monitor a minimal ESP32-S3 project from the controlled workspace | B1.1 | 7 | 8 | 2 | 2 | Me | Minimal project binary, flash log and serial monitor capture | Clean build, flash and target execution succeed |  | 0% | 100% | 1.09% | 0% | 1.09% | Complete | 2026-08-24 | 2026-09-06
B1.3 | B | Engineering Foundation | B1 | Development environment setup | Document workstation setup and onboarding checks | B1.2 | 8 | 8 | 1 | 1 | Me | Developer setup guide and onboarding checklist | A clean workstation can reproduce the setup |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-08-31 | 2026-09-06
B2.1 | B | Engineering Foundation | B2 | Repository initialization | Create production repository structure, .gitignore and component directories | B1.2 | 8 | 8 | 1 | 1 | Me | Initialized repository and directory baseline | Repository builds from a clean clone and generated files are excluded |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-08-31 | 2026-09-06
B2.2 | B | Engineering Foundation | B2 | Repository initialization | Define branching, review, commit, release-tag and semantic-version policies | B2.1 | 9 | 9 | 1 | 1 | Me | Source-control and versioning policy | Release and change-control rules are explicit |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-09-07 | 2026-09-13
B2.3 | B | Engineering Foundation | B2 | Repository initialization | Embed firmware metadata and verify secrets are excluded | B2.2 | 9 | 9 | 1 | 1 | Me | Build metadata output and secret-scan evidence | Binary identifies source/tool versions and no credentials are committed |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-09-07 | 2026-09-13
B3.1 | B | Engineering Foundation | B3 | Build configuration framework | Create debug, validation and production sdkconfig profiles | B2.3 | 9 | 10 | 2 | 2 | Me | Pinned sdkconfig defaults for all profiles | All profiles build and documented differences match policy |  | 0% | 100% | 1.09% | 0% | 1.09% | Complete | 2026-09-07 | 2026-09-20
B3.2 | B | Engineering Foundation | B3 | Build configuration framework | Implement bootstrap, build, flash, erase, monitor and release scripts | B3.1 | 10 | 11 | 2 | 2 | Me | PowerShell/Python build-tool scripts | Scripts operate from a clean checkout without manual path edits |  | 0% | 100% | 1.09% | 0% | 1.09% | Complete | 2026-09-14 | 2026-09-27
B3.3 | B | Engineering Foundation | B3 | Build configuration framework | Add ESP-IDF version guard, image-size checks and deterministic build metadata | B3.2 | 11 | 11 | 1 | 1 | Me | Version-check and image-budget reports | Build fails on wrong toolchain or release-size violation |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-09-21 | 2026-09-27
B4.1 | B | Engineering Foundation | B4 | Continuous integration skeleton | Create CI stages for format, static checks, host tests and profile builds | B3.3 | 11 | 12 | 2 | 2 | Me | CI workflow and successful pipeline run | Every change receives automated checks and build results |  | 0% | 100% | 1.09% | 0% | 1.09% | Complete | 2026-09-21 | 2026-10-04
B4.2 | B | Engineering Foundation | B4 | Continuous integration skeleton | Archive binaries, ELF, MAP, partition table, sdkconfig, logs and test reports | B4.1 | 12 | 12 | 1 | 1 | Me | CI artifact archive | Build outputs are traceable to source revision |  | 0% | 100% | 0.545% | 0% | 0.545% | Complete | 2026-09-28 | 2026-10-04
B4.3 | B | Engineering Foundation | B4 | Continuous integration skeleton | Reproduce clean checkout-to-flash workflow and close Cluster B gate | B1.3,B4.2 | 12 | 12 | 1 | 1.2 | Me | Engineering-baseline gate review | Toolchain, repository, scripts and CI are reproducible | G-B | 0% | 100% | 0.654% | 0% | 0.654% | Complete | 2026-09-28 | 2026-10-04
C1.1 | C | Platform and Architecture Development | C1 | System architecture | Define firmware layers, component groups and dependency direction | B4.3 | 13 | 13 | 1 | 1 | Me | Architecture document and component diagram | Layering prevents product logic from bypassing platform abstractions |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-10-05 | 2026-10-11
C1.2 | C | Platform and Architecture Development | C1 | System architecture | Specify component APIs, ownership, threading, initialization and error contracts | C1.1 | 13 | 14 | 2 | 2 | Me | Component interface specifications | Every mutable resource and interface has a single owner |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-10-05 | 2026-10-18
C1.3 | C | Platform and Architecture Development | C1 | System architecture | Record architecture decisions and review for circular/overlapping responsibilities | C1.2 | 14 | 14 | 1 | 1 | Me | Architecture decision records and review checklist | No circular dependencies or overlapping responsibilities remain |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-10-12 | 2026-10-18
C2.1 | C | Platform and Architecture Development | C2 | Board support package | Define board pins, active levels, pulls, electrical capabilities and revision detection | C1.3 | 15 | 15 | 1 | 1 | Me | Board pin map and revision strategy | All board-specific data is isolated in the BSP |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-10-19 | 2026-10-25
C2.2 | C | Platform and Architecture Development | C2 | Board support package | Implement safe startup, peripheral power sequencing and bus initialization | C2.1 | 15 | 16 | 2 | 2 | Me | Board initialization code and startup-sequence trace | Startup drives no unsafe outputs and buses initialize deterministically |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-10-19 | 2026-11-01
C2.3 | C | Platform and Architecture Development | C2 | Board support package | Build board self-test for GPIO, buttons, LED, I2C, SPI, OLED, SX1262, ADC and Vext | C2.2 | 16 | 17 | 2 | 2 | Me | Board self-test application and pass report | Every board peripheral is independently verified |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-10-26 | 2026-11-08
C3.1 | C | Platform and Architecture Development | C3 | HAL and device drivers | Implement HAL wrappers for GPIO, I2C, SPI, UART, ADC, PWM, timers and power | C2.2 | 18 | 19 | 2 | 2 | Me | HAL components and API documentation | Application and drivers use HAL contracts rather than raw peripheral calls |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-11-09 | 2026-11-22
C3.2 | C | Platform and Architecture Development | C3 | HAL and device drivers | Implement core sensor, actuator, LED and button drivers with structured errors | C3.1 | 19 | 20 | 2 | 2 | Me | Core device-driver components and unit tests | Normal, invalid-input, timeout and missing-device paths are covered |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-11-16 | 2026-11-29
C3.3 | C | Platform and Architecture Development | C3 | HAL and device drivers | Implement OLED, SX1262 and battery-monitor drivers | C3.1,C2.3 | 20 | 21 | 2 | 2 | Me | Display, radio and battery driver test applications | Drivers initialize and recover from communication faults |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-11-23 | 2026-12-06
C3.4 | C | Platform and Architecture Development | C3 | HAL and device drivers | Run bus recovery, repeated-init and ownership/concurrency tests | C3.2,C3.3 | 21 | 21 | 1 | 1 | Me | Driver fault-injection report | Peripheral access is serialized and structured errors propagate |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-11-30 | 2026-12-06
C4.1 | C | Platform and Architecture Development | C4 | Flash, bootloader, and partition architecture | Design 8 MB partition table and warning/release/hard image budgets | C1.3 | 15 | 16 | 2 | 2 | Me | Production partition CSV and size-budget rationale | All partitions fit and both OTA slots accept the release limit |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-10-19 | 2026-11-01
C4.2 | C | Platform and Architecture Development | C4 | Flash, bootloader, and partition architecture | Define boot selection, trial-boot, rollback and recovery-entry flows | C4.1 | 17 | 17 | 1 | 1 | Me | Boot-flow and recovery-flow diagrams | All boot and recovery paths have deterministic entry criteria |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-11-02 | 2026-11-08
C4.3 | C | Platform and Architecture Development | C4 | Flash, bootloader, and partition architecture | Implement recovery application skeleton and partition inspection | C4.2,C3.1 | 18 | 18 | 1 | 1 | Me | Bootable recovery image | Recovery starts independently and exposes essential diagnostics |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-11-09 | 2026-11-15
C4.4 | C | Platform and Architecture Development | C4 | Flash, bootloader, and partition architecture | Validate partition offsets, maximum images and migration constraints | C4.3 | 18 | 18 | 1 | 1 | Me | Partition validation report | Physical flash layout and upgrade constraints are verified |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-11-09 | 2026-11-15
C5.1 | C | Platform and Architecture Development | C5 | Startup and service supervision | Implement early startup, reset capture, NVS/config/identity load and board initialization | C3.4,C4.4 | 22 | 22 | 1 | 1 | Me | Minimal app_main and early-startup trace | Initialization order is deterministic and failures are recorded |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-12-07 | 2026-12-13
C5.2 | C | Platform and Architecture Development | C5 | Startup and service supervision | Implement startup state machine and service result model | C5.1 | 22 | 23 | 2 | 2 | Me | Startup coordinator and supervisor | Services report OK, degraded, retryable or fatal outcomes |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-12-07 | 2026-12-20
C5.3 | C | Platform and Architecture Development | C5 | Startup and service supervision | Implement boot-loop persistence, safe mode and recovery escalation | C5.2 | 23 | 24 | 2 | 2 | Me | Boot-failure policy and safe-mode implementation | Repeated failures do not cause endless rebooting |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-12-14 | 2026-12-27
C5.4 | C | Platform and Architecture Development | C5 | Startup and service supervision | Test normal, degraded, fatal and recovery startup paths | C5.3 | 24 | 24 | 1 | 1 | Me | Startup-path test report | All startup outcomes reach bounded, diagnosable states |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-12-21 | 2026-12-27
C6.1 | C | Platform and Architecture Development | C6 | RTOS task and event architecture | Define RTOS task ownership, priorities, stack budgets and liveness conditions | C1.3 | 22 | 22 | 1 | 1 | Me | Task architecture and priority/stack table | Every task has one responsibility and measurable liveness |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-12-07 | 2026-12-13
C6.2 | C | Platform and Architecture Development | C6 | RTOS task and event architecture | Implement typed commands/events, bounded queues, notifications and timers | C6.1 | 23 | 24 | 2 | 2 | Me | Queue/event catalogue and messaging framework | All buffers are bounded with overflow policy and diagnostics |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-12-14 | 2026-12-27
C6.3 | C | Platform and Architecture Development | C6 | RTOS task and event architecture | Configure stack monitoring, watchdog participation and blocking-time limits | C6.2,C5.2 | 24 | 25 | 2 | 2 | Me | Runtime stack/watchdog metrics | Stack margins and watchdog policies are observable |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2026-12-21 | 2027-01-03
C6.4 | C | Platform and Architecture Development | C6 | RTOS task and event architecture | Stress queues, notifications, ISR handoff and concurrent service ownership | C6.3 | 25 | 25 | 1 | 1 | Me | RTOS concurrency test report | No unbounded growth, starvation or ownership violation is observed |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2026-12-28 | 2027-01-03
C7.1 | C | Platform and Architecture Development | C7 | Persistent storage platform | Classify factory identity, user config, operational state and bulk data; define schemas | C5.1 | 26 | 26 | 1 | 1 | Me | Data classification and versioned schema specification | Persisted formats are explicit and versioned |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-01-04 | 2027-01-10
C7.2 | C | Platform and Architecture Development | C7 | Persistent storage platform | Implement configuration service with integrity and atomic activation | C7.1 | 26 | 27 | 2 | 2 | Me | Configuration service and atomic-update tests | Interrupted writes preserve the previous valid configuration |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-01-04 | 2027-01-17
C7.3 | C | Platform and Architecture Development | C7 | Persistent storage platform | Implement migrations, filesystem rotation, full-storage and cleanup behavior | C7.2 | 27 | 28 | 2 | 2 | Me | Migration functions and filesystem service | Sequential migration and full-storage behavior are deterministic |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-01-11 | 2027-01-24
C7.4 | C | Platform and Architecture Development | C7 | Persistent storage platform | Execute storage corruption and power-loss tests | C7.3 | 28 | 28 | 1 | 1 | Me | Storage power-loss and recovery report | Persistent data remains valid or recoverable |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-01-18 | 2027-01-24
C8.1 | C | Platform and Architecture Development | C8 | Diagnostics and health monitoring | Implement structured logging and stable event-ID catalogue | C5.2 | 29 | 29 | 1 | 1 | Me | Logging framework and event catalogue | Logs use consistent fields and contain no sensitive values |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-01-25 | 2027-01-31
C8.2 | C | Platform and Architecture Development | C8 | Diagnostics and health monitoring | Implement diagnostic snapshot for versions, reset, heap, stacks, network and storage | C8.1,C6.3,C7.4 | 29 | 30 | 2 | 2 | Me | Health-monitor service and snapshot output | Required support metrics are retrievable on demand |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-01-25 | 2027-02-07
C8.3 | C | Platform and Architecture Development | C8 | Diagnostics and health monitoring | Enable watchdog layers, core-dump partition and pre-crash event buffer | C8.2,C4.4 | 30 | 31 | 2 | 2 | Me | Watchdog/core-dump configuration and captured sample fault | Crash evidence can be matched to retained ELF symbols |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-02-01 | 2027-02-14
C8.4 | C | Platform and Architecture Development | C8 | Diagnostics and health monitoring | Document core-dump retrieval and diagnostic triage workflow | C8.3 | 31 | 31 | 1 | 1 | Me | Field diagnostic and core-dump guide | A fault can be captured, decoded and linked to a build |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-02-08 | 2027-02-14
C.G1 | C | Platform and Architecture Development | C8 | Diagnostics and health monitoring | Integrate board, drivers, storage, startup, RTOS and diagnostics into platform baseline | C5.4,C6.4,C7.4,C8.4 | 32 | 33 | 2 | 2.6 | Me | Integrated platform build and interface test report | Platform services run together without product-specific coupling | G-C | 0% | 0% | 1.417% | 0% | 0% | Not Started | 2027-02-15 | 2027-02-28
C.G2 | C | Platform and Architecture Development | C8 | Diagnostics and health monitoring | Run 72-hour platform soak, close blockers and approve Cluster C gate | C.G1 | 33 | 34 | 2 | 2.6 | Me | Soak report, defect closure list and platform-baseline approval | No unexplained reset, heap drift or critical open defect remains | G-C | 0% | 0% | 1.417% | 0% | 0% | Not Started | 2027-02-22 | 2027-03-07
D1.1 | D | Product Feature Development | D1 | Product state machine | Define device states, product commands and events | C.G2 | 35 | 35 | 1 | 1 | Me | Product state diagram and command/event catalogue | All mandatory product modes map to explicit states |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-03-08 | 2027-03-14
D1.2 | D | Product Feature Development | D1 | Product state machine | Implement transition handlers, timeouts, failure paths and persistent state | D1.1 | 36 | 36 | 1 | 1 | Me | State transition table and implementation | Transitions are deterministic with defined unexpected-event behavior |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-03-15 | 2027-03-21
D1.3 | D | Product Feature Development | D1 | Product state machine | Unit-test normal, degraded, maintenance, update, safe and recovery transitions | D1.2 | 37 | 37 | 1 | 1 | Me | State-machine unit-test report | Critical transitions and invalid-event paths pass |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-03-22 | 2027-03-28
D2.1 | D | Product Feature Development | D2 | Connectivity services | Implement single-owner Wi-Fi network manager and lifecycle states | D1.3 | 38 | 38 | 1 | 1 | Me | Network manager component | Only the network manager controls Wi-Fi |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-03-29 | 2027-04-04
D2.2 | D | Product Feature Development | D2 | Connectivity services | Implement selected provisioning and authorized reset workflow | D2.1 | 39 | 39 | 1 | 1 | Me | Provisioning service and provisioning test logs | Fresh and reset devices provision successfully |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-04-05 | 2027-04-11
D2.3 | D | Product Feature Development | D2 | Connectivity services | Implement exponential backoff with jitter and connection diagnostics | D2.2 | 40 | 40 | 1 | 1 | Me | Retry/backoff implementation and metrics | Reconnect storms are prevented and reasons are recorded |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-04-12 | 2027-04-18
D2.4 | D | Product Feature Development | D2 | Connectivity services | Test long-duration network loss, recovery and repeated provisioning | D2.3 | 40 | 40 | 1 | 1 | Me | Connectivity resilience report | Extended outages do not destabilize memory, storage or state |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-04-12 | 2027-04-18
D3.1 | D | Product Feature Development | D3 | LoRa and LoRaWAN services | Integrate SX1262 reset, busy, DIO, frequency, power, sleep and wake behavior | C3.3,D1.3 | 41 | 42 | 2 | 2 | Me | Radio service and radio test logs | Radio configuration and interrupt paths are stable |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-04-19 | 2027-05-02
D3.2 | D | Product Feature Development | D3 | LoRa and LoRaWAN services | Integrate LoRaWAN OTAA join, uplink, downlink, ADR and retry scheduling | D3.1 | 42 | 43 | 2 | 2 | Me | LoRaWAN manager and network-server test evidence | Join and message exchange succeed reliably |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-04-26 | 2027-05-09
D3.3 | D | Product Feature Development | D3 | LoRa and LoRaWAN services | Persist frame counters and enforce region/key handling rules | D3.2,C7.4 | 43 | 44 | 2 | 2 | Me | Counter persistence and regional compliance tests | Reset cannot cause prohibited counter reuse or region mismatch |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-05-03 | 2027-05-16
D3.4 | D | Product Feature Development | D3 | LoRa and LoRaWAN services | Run long-duration join/uplink/downlink stability test | D3.3 | 44 | 44 | 1 | 1 | Me | LoRaWAN endurance report | Long-run operation meets reliability and duty-cycle requirements |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-05-10 | 2027-05-16
D4.1 | D | Product Feature Development | D4 | Cloud and transport services | Define transport abstraction and versioned telemetry schema | D1.3 | 45 | 45 | 1 | 1 | Me | Transport API and telemetry specification | Product logic is independent of MQTT/HTTP specifics |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-05-17 | 2027-05-23
D4.2 | D | Product Feature Development | D4 | Cloud and transport services | Implement cloud client, certificate validation and response handling | D2.4,D4.1 | 46 | 46 | 1 | 1 | Me | Cloud client and integration logs | Valid sessions work and invalid server responses are rejected safely |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-05-24 | 2027-05-30
D4.3 | D | Product Feature Development | D4 | Cloud and transport services | Implement bounded offline spool, retry, expiry and deduplication | D4.2,C7.4 | 46 | 47 | 2 | 2 | Me | Offline queue and backlog test evidence | Cloud outages cannot exhaust memory or storage |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-05-24 | 2027-06-06
D4.4 | D | Product Feature Development | D4 | Cloud and transport services | Test disconnects, invalid payloads, backlog replay and throttling | D4.3 | 47 | 47 | 1 | 1 | Me | Cloud outage and replay report | Documented data-loss and recovery behavior is verified |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-05-31 | 2027-06-06
D5.1 | D | Product Feature Development | D5 | Product sensing and control | Implement acquisition validation, calibration, normalization and filtering pipeline | D1.3,C3.2 | 38 | 39 | 2 | 2 | Me | Acquisition service and sample-quality tests | Invalid raw data is rejected before product decisions |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-03-29 | 2027-04-11
D5.2 | D | Product Feature Development | D5 | Product sensing and control | Implement control rules, hysteresis, timing, safety limits and manual override | D5.1 | 39 | 40 | 2 | 2 | Me | Control service and rule-test report | Only one service writes actuator states |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-04-05 | 2027-04-18
D5.3 | D | Product Feature Development | D5 | Product sensing and control | Implement calibration storage, validity, migration and corrupt-data fallback | D5.1,C7.4 | 41 | 41 | 1 | 1 | Me | Calibration service and migration tests | Corrupt calibration cannot produce unsafe output |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-04-19 | 2027-04-25
D5.4 | D | Product Feature Development | D5 | Product sensing and control | Verify control timing, boundaries and safe-output states | D5.2,D5.3 | 42 | 42 | 1 | 1 | Me | Algorithm, latency and safe-state test report | Control and timing requirements pass under boundary inputs |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-04-26 | 2027-05-02
D6.1 | D | Product Feature Development | D6 | Power management | Define active, idle, sleep, charging and battery-critical states | D4.4,D5.4 | 48 | 48 | 1 | 1 | Me | Power-state model | All power transitions have entry/exit criteria |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-06-07 | 2027-06-13
D6.2 | D | Product Feature Development | D6 | Power management | Implement sleep coordinator, state save, peripheral shutdown and wake handling | D6.1 | 49 | 49 | 1 | 1 | Me | Sleep/wake implementation and traces | Critical transactions complete before sleep and wake state is valid |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-06-14 | 2027-06-20
D6.3 | D | Product Feature Development | D6 | Power management | Measure boot, active, Wi-Fi, LoRa, idle and sleep currents; estimate battery life | D6.2 | 50 | 50 | 1 | 1 | Me | Power-consumption report and battery-life estimate | Measured current remains within approved budget |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-06-21 | 2027-06-27
D6.4 | D | Product Feature Development | D6 | Power management | Run repeated sleep/wake and low-battery behavior tests | D6.3 | 50 | 50 | 1 | 1 | Me | Power-cycle repeatability report | Cycles are repeatable without state corruption |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-06-21 | 2027-06-27
D7.1 | D | Product Feature Development | D7 | OTA update and recovery | Define signed OTA manifest, compatibility and secure-version policy | D4.4,D8.1 | 51 | 51 | 1 | 1 | Me | OTA manifest specification | Product, hardware, version, size, hash and signature rules are explicit |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-06-28 | 2027-07-04
D7.2 | D | Product Feature Development | D7 | OTA update and recovery | Implement manifest fetch, download, cryptographic verification and staging | D7.1 | 51 | 52 | 2 | 2 | Me | OTA client and verifier tests | Corrupt, oversized or incompatible images are rejected |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-06-28 | 2027-07-11
D7.3 | D | Product Feature Development | D7 | OTA update and recovery | Implement trial-boot acceptance, rollback and boot-loop interaction | D7.2,C5.3 | 53 | 53 | 1 | 1 | Me | Trial-boot and rollback evidence | Failed trial boot automatically returns to a valid image |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-07-12 | 2027-07-18
D7.4 | D | Product Feature Development | D7 | OTA update and recovery | Complete recovery installer and test power loss during OTA paths | D7.3,C4.3 | 54 | 54 | 1 | 1 | Me | Recovery application and OTA power-loss matrix | Power loss cannot brick the device and recovery reinstalls a signed image |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-07-19 | 2027-07-25
D8.1 | D | Product Feature Development | D8 | Security implementation | Finalize security architecture, assets, trust boundaries and attack surfaces | C.G2 | 35 | 36 | 2 | 2 | Me | Updated threat model and security architecture | Security requirements are allocated to implementation and tests |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-03-08 | 2027-03-21
D8.2 | D | Product Feature Development | D8 | Security implementation | Define per-device identity, key management, signing, eFuse and debug policies | D8.1 | 43 | 44 | 2 | 2 | Me | Key-management procedure and eFuse/debug plan | Development, validation and production security states are separated |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-05-03 | 2027-05-16
D8.3 | D | Product Feature Development | D8 | Security implementation | Integrate secure boot, flash/NVS encryption, TLS validation and log redaction on validation hardware | D8.2,D7.2 | 53 | 54 | 2 | 2 | Me | Security-validation build and configuration evidence | Authenticity and confidentiality controls operate together |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-07-12 | 2027-07-25
D8.4 | D | Product Feature Development | D8 | Security implementation | Implement security failure handling and verify unauthorized workflows fail | D8.3 | 54 | 54 | 1 | 1 | Me | Security failure-path test report | Invalid signatures, identity faults and unauthorized resets are bounded |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-07-19 | 2027-07-25
D.G1 | D | Product Feature Development | D1 | Product state machine | Integrate product state, connectivity, LoRaWAN, cloud, sensing, power, OTA and security | D2.4,D3.4,D4.4,D5.4,D6.4,D7.4,D8.4 | 55 | 55 | 1 | 1.4 | Me | Feature-complete integrated build and system smoke report | All mandatory features operate together | G-D | 0% | 0% | 0.7629% | 0% | 0% | Not Started | 2027-07-26 | 2027-08-01
D.G2 | D | Product Feature Development | D1 | Product state machine | Close feature blockers and approve Cluster D gate | D.G1 | 56 | 56 | 1 | 1.4 | Me | Feature-complete gate review and defect disposition | No critical feature remains prototype-only | G-D | 0% | 0% | 0.7629% | 0% | 0% | Not Started | 2027-08-02 | 2027-08-08
E1.1 | E | Verification and Qualification | E1 | Static verification | Enforce warning policy, formatting, naming, headers and API documentation | D.G2 | 57 | 57 | 1 | 1 | Me | Compiler/style report | Selected warnings are errors and style violations are resolved |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-08-09 | 2027-08-15
E1.2 | E | Verification and Qualification | E1 | Static verification | Run static analysis for memory, integer, locking, resource and return-value defects | E1.1 | 58 | 58 | 1 | 1 | Me | Static-analysis report | No unresolved critical finding remains |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-08-16 | 2027-08-22
E1.3 | E | Verification and Qualification | E1 | Static verification | Review complexity, dead code, duplicate code and approved deviations | E1.2 | 58 | 58 | 1 | 1 | Me | Code-review record and deviation register | All deviations are documented and accepted |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-08-16 | 2027-08-22
E2.1 | E | Verification and Qualification | E2 | Unit and component testing | Expand host tests for state machines, parsers, serialization, migration, retry and algorithms | D.G2 | 57 | 58 | 2 | 2 | Me | Host unit-test suite and report | Critical pure logic and error paths pass |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2027-08-09 | 2027-08-22
E2.2 | E | Verification and Qualification | E2 | Unit and component testing | Run target unit tests for storage, drivers, queues, timers, network and OTA managers | E2.1 | 59 | 59 | 1 | 1 | Me | Target component-test report | ESP-IDF-dependent components pass on hardware |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-08-23 | 2027-08-29
E2.3 | E | Verification and Qualification | E2 | Unit and component testing | Complete mocks/fakes, practical coverage review and CI automation | E2.2 | 60 | 60 | 1 | 1 | Me | Test doubles, coverage summary and automated test job | Tests are repeatable in CI or controlled hardware |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-08-30 | 2027-09-05
E3.1 | E | Verification and Qualification | E3 | Integration testing | Test startup/storage, driver/acquisition, event/state, network/cloud and OTA/supervisor integration | E2.3 | 61 | 61 | 1 | 1 | Me | Platform integration-test report | All defined component interfaces are exercised |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-09-06 | 2027-09-12
E3.2 | E | Verification and Qualification | E3 | Integration testing | Inject bus timeout, disconnect, invalid message, storage full, corruption and missing peripheral | E3.1 | 62 | 62 | 1 | 1 | Me | Interface-failure test results | Failure propagation follows architecture and ownership rules |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-09-13 | 2027-09-19
E3.3 | E | Verification and Qualification | E3 | Integration testing | Update requirement-to-test traceability and defect records | E3.2 | 62 | 62 | 1 | 1 | Me | Updated RTM and defect list | Every release requirement has current verification status |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-09-13 | 2027-09-19
E4.1 | E | Verification and Qualification | E4 | System and hardware-in-loop testing | Build HIL control for power, reset, GPIO, serial logs and network interruption | E3.3 | 63 | 63 | 1 | 1 | Me | HIL framework and automation scripts | Target stimuli and evidence capture are repeatable |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-09-20 | 2027-09-26
E4.2 | E | Verification and Qualification | E4 | System and hardware-in-loop testing | Run factory reset-to-provisioning-to-operation-to-OTA end-to-end scenarios | E4.1 | 64 | 64 | 1 | 1 | Me | End-to-end system-test report | Required product scenarios pass without manual intervention |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-09-27 | 2027-10-03
E4.3 | E | Verification and Qualification | E4 | System and hardware-in-loop testing | Run 24-hour smoke, multi-day stability, reboot, provisioning, sleep and backlog tests | E4.2 | 65 | 65 | 1 | 1 | Me | Long-duration report and stability metrics | No unexplained reset, heap drift or unbounded queue growth occurs |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-10-04 | 2027-10-10
E5.1 | E | Verification and Qualification | E5 | Robustness and fault-injection testing | Interrupt power during storage writes, migration, OTA switch, trial boot and provisioning | E4.2 | 65 | 65 | 1 | 1 | Me | Power-loss test report | Persistent data and bootability remain valid or recoverable |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-10-04 | 2027-10-10
E5.2 | E | Verification and Qualification | E5 | Robustness and fault-injection testing | Inject network, DNS, TLS, authentication, LoRaWAN and cloud server failures | E5.1 | 66 | 66 | 1 | 1 | Me | Communication fault-injection report | Recovery time and retry behavior remain bounded |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-10-11 | 2027-10-17
E5.3 | E | Verification and Qualification | E5 | Robustness and fault-injection testing | Test low/fragmented heap, full queues/filesystem, rapid events, task stalls and deadlocks | E5.2 | 67 | 67 | 1 | 1 | Me | Resource/watchdog fault report | Watchdog recovery produces useful diagnostics and no expected fault bricks the unit |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-10-18 | 2027-10-24
E6.1 | E | Verification and Qualification | E6 | Performance and resource qualification | Measure heap, fragmentation, internal/DMA memory, stacks, CPU load and idle margin | E5.3 | 68 | 68 | 1 | 1 | Me | Memory and CPU qualification report | Resource use remains below approved limits under worst-case load |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-10-25 | 2027-10-31
E6.2 | E | Verification and Qualification | E6 | Performance and resource qualification | Verify image sizes, filesystem reserve, boot/join/control/OTA/recovery timing | E6.1 | 68 | 68 | 1 | 1 | Me | Flash and timing qualification report | Release image and all timing budgets pass |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-10-25 | 2027-10-31
E7.1 | E | Verification and Qualification | E7 | Security validation | Verify unsigned/modified/wrong-product/wrong-hardware/old-version image rejection and rollback | E6.2,D8.4 | 69 | 69 | 1 | 1 | Me | Firmware and storage security-validation report | Authenticity, anti-rollback and encrypted-storage controls pass |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-11-01 | 2027-11-07
E7.2 | E | Verification and Qualification | E7 | Security validation | Verify certificates, hostname, auth failures, debug restrictions and recovery authorization | E7.1 | 69 | 69 | 1 | 1 | Me | Communication/interface security report | Unauthorized commands and invalid trust chains fail safely |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-11-01 | 2027-11-07
E.G1 | E | Verification and Qualification | E7 | Security validation | Close critical/high defects, freeze release candidate and approve Cluster E gate | E1.3,E3.3,E4.3,E5.3,E6.2,E7.2 | 70 | 70 | 1 | 1.5 | Me | Release-candidate approval, reproducible build and residual-risk record | All requirements have evidence and critical/high defects are closed or accepted | G-E | 0% | 0% | 0.8174% | 0% | 0% | Not Started | 2027-11-08 | 2027-11-14
F1.1 | F | Industrialization and Production Release | F1 | Manufacturing test system | Implement manufacturing firmware covering flash, RAM, GPIO, UI, buses, radio, wireless, ADC and identity | E.G1 | 71 | 71 | 1 | 1 | Me | Manufacturing-test application and coverage matrix | Every production-critical hardware function has a pass/fail test |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-11-15 | 2027-11-21
F1.2 | F | Industrialization and Production Release | F1 | Manufacturing test system | Develop station software, fixture control, programming and result capture | F1.1 | 72 | 72 | 1 | 1 | Me | Manufacturing station software and fixture test | Station programs, tests and records units repeatably |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-11-22 | 2027-11-28
F1.3 | F | Industrialization and Production Release | F1 | Manufacturing test system | Define traceability record, retest, repair and fail containment | F1.2 | 73 | 73 | 1 | 1 | Me | Manufacturing record schema and retest procedure | Failed units cannot pass silently and every unit is traceable |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-11-29 | 2027-12-05
F2.1 | F | Industrialization and Production Release | F2 | Security provisioning and eFuse control | Implement controlled identity, certificate and security provisioning sequence | F1.3,D8.2 | 73 | 73 | 1 | 1 | Me | Provisioning workflow and audit record | Identity is verified before irreversible operations |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-11-29 | 2027-12-05
F2.2 | F | Industrialization and Production Release | F2 | Security provisioning and eFuse control | Implement eFuse programming with preconditions, readback and failure recovery | F2.1 | 74 | 74 | 1 | 1 | Me | eFuse script and irreversible-operation checklist | Every irreversible write is logged and verified |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-12-06 | 2027-12-12
F2.3 | F | Industrialization and Production Release | F2 | Security provisioning and eFuse control | Reboot and verify secure boot, flash encryption and final production state | F2.2 | 74 | 74 | 1 | 1 | Me | Post-provisioning security-state report | Locked production configuration is independently verified |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-12-06 | 2027-12-12
F3.1 | F | Industrialization and Production Release | F3 | Release packaging | Package application, recovery, bootloader, partitions, OTA/factory images, ELF, MAP and checksums | F2.3 | 75 | 75 | 1 | 1 | Me | Signed release package | All artifacts correspond to the same approved source |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-12-13 | 2027-12-19
F3.2 | F | Industrialization and Production Release | F3 | Release packaging | Create manifest, SBOM, release notes, dependency lock and retention archive | F3.1 | 75 | 75 | 1 | 1 | Me | Release manifest, SBOM, notes and archived symbols | Hashes verify and tagged source reproduces the release |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-12-13 | 2027-12-19
F4.1 | F | Industrialization and Production Release | F4 | Pilot production and deployment | Run pilot batch using final board, fixture, provisioning, security and package process | F3.2 | 76 | 76 | 1 | 1 | Me | Pilot production report | Pilot units complete the final manufacturing flow |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-12-20 | 2027-12-26
F4.2 | F | Industrialization and Production Release | F4 | Pilot production and deployment | Monitor yield, RF, boot, OTA, battery, reset and cloud behavior | F4.1 | 77 | 77 | 1 | 1 | Me | Yield and field-trial metrics | Pilot metrics meet release thresholds |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2027-12-27 | 2028-01-02
F4.3 | F | Industrialization and Production Release | F4 | Pilot production and deployment | Conduct go/no-go review for defects, yield, security, rollback and support readiness | F4.2 | 78 | 78 | 1 | 1.5 | Me | Production-release approval record | Manufacturing, support and rollback readiness are accepted | G-F | 0% | 0% | 0.8174% | 0% | 0% | Not Started | 2028-01-03 | 2028-01-09
F.G1 | F | Industrialization and Production Release | F4 | Pilot production and deployment | Tag and release production firmware; archive complete evidence package | F4.3 | 78 | 78 | 1 | 1.5 | Me | Production tag, signed artifacts and permanent evidence archive | Approved production release is reproducible and recoverable | G-F | 0% | 0% | 0.8174% | 0% | 0% | Not Started | 2028-01-03 | 2028-01-09
G1.1 | G | Field Operation and Lifecycle Maintenance | G1 | Field monitoring | Deploy health dashboard for versions, resets, boot loops, OTA, connectivity, heap, storage and watchdogs | F.G1 | 79 | 79 | 1 | 1 | Me | Device-health dashboard and metric definitions | Fleet health is visible by firmware and hardware revision |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2028-01-10 | 2028-01-16
G1.2 | G | Field Operation and Lifecycle Maintenance | G1 | Field monitoring | Set alert thresholds and publish support diagnostic procedure | G1.1 | 80 | 80 | 1 | 1 | Me | Alert rules and support guide | Operational anomalies create actionable alerts |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2028-01-17 | 2028-01-23
G2.1 | G | Field Operation and Lifecycle Maintenance | G2 | Defect and incident management | Define severity, incident intake, triage, core-dump and root-cause workflow | F.G1 | 79 | 79 | 1 | 1 | Me | Incident-management procedure and templates | Critical-to-low incidents have explicit handling |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2028-01-10 | 2028-01-16
G2.2 | G | Field Operation and Lifecycle Maintenance | G2 | Defect and incident management | Rehearse hotfix, regression, rollback and controlled release workflow | G2.1 | 80 | 81 | 2 | 2 | Me | Hotfix rehearsal report | A field defect can be corrected and rolled back safely |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2028-01-17 | 2028-01-30
G2.3 | G | Field Operation and Lifecycle Maintenance | G2 | Defect and incident management | Operate incident review and corrective-action loop during stabilization | G2.2 | 82 | 90 | 9 | 6.3 | Me | Incident log, RCA and corrective-action records | Field issues are classified, traced and closed with regression evidence |  | 0% | 0% | 3.433% | 0% | 0% | Not Started | 2028-01-31 | 2028-04-02
G3.1 | G | Field Operation and Lifecycle Maintenance | G3 | Controlled OTA rollout | Roll out to internal and engineering fleets; monitor stop criteria | F.G1,G1.1 | 79 | 79 | 1 | 1 | Me | Internal rollout report | No threshold breach before external exposure |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2028-01-10 | 2028-01-16
G3.2 | G | Field Operation and Lifecycle Maintenance | G3 | Controlled OTA rollout | Roll out to pilot customers and small production percentage | G3.1 | 80 | 81 | 2 | 2 | Me | Pilot rollout dashboard and decision record | Download, trial and rollback metrics remain acceptable |  | 0% | 0% | 1.09% | 0% | 0% | Not Started | 2028-01-17 | 2028-01-30
G3.3 | G | Field Operation and Lifecycle Maintenance | G3 | Controlled OTA rollout | Expand staged rollout to larger percentages and full fleet | G3.2 | 82 | 84 | 3 | 3 | Me | Full rollout report | Rollout completes without stop-condition breach |  | 0% | 0% | 1.635% | 0% | 0% | Not Started | 2028-01-31 | 2028-02-20
G4.1 | G | Field Operation and Lifecycle Maintenance | G4 | Framework and dependency upgrades | Assess framework/dependency security fixes, support dates, APIs, bootloader, size and radio impact | G3.3 | 85 | 85 | 1 | 1 | Me | Upgrade-impact report | Upgrade risks and required migrations are identified |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2028-02-21 | 2028-02-27
G4.2 | G | Field Operation and Lifecycle Maintenance | G4 | Framework and dependency upgrades | Run clean build, storage, OTA, rollback, power-loss, security, performance and endurance regression | G4.1 | 86 | 86 | 1 | 1 | Me | Dependency-upgrade regression report | Upgrade preserves release requirements |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2028-02-28 | 2028-03-05
G5.1 | G | Field Operation and Lifecycle Maintenance | G5 | Hardware revision support | Define hardware compatibility matrix and update board revision detection/BSP | G4.2 | 87 | 87 | 1 | 1 | Me | Hardware compatibility matrix and BSP update | Firmware compatibility range is explicit |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2028-03-06 | 2028-03-12
G5.2 | G | Field Operation and Lifecycle Maintenance | G5 | Hardware revision support | Test peripherals, boot, RF and OTA across supported revisions; reject incompatible images | G5.1 | 88 | 88 | 1 | 1 | Me | Hardware-revision qualification report | Compatible revisions pass and incompatible images are rejected |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2028-03-13 | 2028-03-19
G6.1 | G | Field Operation and Lifecycle Maintenance | G6 | End-of-life | Define final firmware, signing-key, cloud shutdown, credential revocation and retention policy | G5.2 | 89 | 89 | 1 | 1 | Me | End-of-life policy | Service, security and archival obligations have defined endpoints |  | 0% | 0% | 0.545% | 0% | 0% | Not Started | 2028-03-20 | 2028-03-26
G6.2 | G | Field Operation and Lifecycle Maintenance | G6 | End-of-life | Archive final firmware/tools/records and complete product-closure review | G6.1,G2.3 | 90 | 90 | 1 | 1.3 | Me | Product-closure package and approval | Final artifacts and responsibilities are formally closed | G-G | 0% | 0% | 0.7084% | 0% | 0% | Not Started | 2028-03-27 | 2028-04-02

## Phase Summary
Phase-Level Summary
Phase | Cluster | Phase Name | Start Week | End Week | Owner | Planned % | Actual % | Variance | Work Packages | Complete | Phase Status
A1 | A | Product concept definition | 1 | 2 | Me | 50% | 100% | 50% | 3 | 3 | Complete
A2 | A | Requirements engineering | 2 | 4 | Me | 0% | 100% | 100% | 4 | 4 | Complete
A3 | A | Feasibility and risk analysis | 4 | 6 | Me | 0% | 100% | 100% | 3 | 3 | Complete
B1 | B | Development environment setup | 7 | 8 | Me | 0% | 100% | 100% | 3 | 3 | Complete
B2 | B | Repository initialization | 8 | 9 | Me | 0% | 100% | 100% | 3 | 3 | Complete
B3 | B | Build configuration framework | 9 | 11 | Me | 0% | 100% | 100% | 3 | 3 | Complete
B4 | B | Continuous integration skeleton | 11 | 12 | Me | 0% | 100% | 100% | 3 | 3 | Complete
C1 | C | System architecture | 13 | 14 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
C2 | C | Board support package | 15 | 17 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
C3 | C | HAL and device drivers | 18 | 21 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
C4 | C | Flash, bootloader, and partition architecture | 15 | 18 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
C5 | C | Startup and service supervision | 22 | 24 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
C6 | C | RTOS task and event architecture | 22 | 25 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
C7 | C | Persistent storage platform | 26 | 28 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
C8 | C | Diagnostics and health monitoring | 29 | 34 | Me | 0% | 0% | 0% | 6 | 0 | Not Started
D1 | D | Product state machine | 35 | 56 | Me | 0% | 0% | 0% | 5 | 0 | Not Started
D2 | D | Connectivity services | 38 | 40 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
D3 | D | LoRa and LoRaWAN services | 41 | 44 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
D4 | D | Cloud and transport services | 45 | 47 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
D5 | D | Product sensing and control | 38 | 42 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
D6 | D | Power management | 48 | 50 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
D7 | D | OTA update and recovery | 51 | 54 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
D8 | D | Security implementation | 35 | 54 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
E1 | E | Static verification | 57 | 58 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
E2 | E | Unit and component testing | 57 | 60 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
E3 | E | Integration testing | 61 | 62 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
E4 | E | System and hardware-in-loop testing | 63 | 65 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
E5 | E | Robustness and fault-injection testing | 65 | 67 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
E6 | E | Performance and resource qualification | 68 | 68 | Me | 0% | 0% | 0% | 2 | 0 | Not Started
E7 | E | Security validation | 69 | 70 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
F1 | F | Manufacturing test system | 71 | 73 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
F2 | F | Security provisioning and eFuse control | 73 | 74 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
F3 | F | Release packaging | 75 | 75 | Me | 0% | 0% | 0% | 2 | 0 | Not Started
F4 | F | Pilot production and deployment | 76 | 78 | Me | 0% | 0% | 0% | 4 | 0 | Not Started
G1 | G | Field monitoring | 79 | 80 | Me | 0% | 0% | 0% | 2 | 0 | Not Started
G2 | G | Defect and incident management | 79 | 90 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
G3 | G | Controlled OTA rollout | 79 | 84 | Me | 0% | 0% | 0% | 3 | 0 | Not Started
G4 | G | Framework and dependency upgrades | 85 | 86 | Me | 0% | 0% | 0% | 2 | 0 | Not Started
G5 | G | Hardware revision support | 87 | 88 | Me | 0% | 0% | 0% | 2 | 0 | Not Started
G6 | G | End-of-life | 89 | 90 | Me | 0% | 0% | 0% | 2 | 0 | Not Started

## Weekly Plan
90-Week Solo Execution Plan
Week | Week Start | Week Finish | Active WBS IDs | Weekly Focus | Evidence Due | Gate / Milestone | Planned Cumulative % | Actual Snapshot
1 | 2026-07-13 | 2026-07-19 | A1.1, A1.2 | A1.1: Define users, operating environment, installation, power, connectivity, UI, maintenance and update strategy A1.2: Model normal and abnormal operating scenarios | A1.1: Product concept document and primary use-case list |  | 1.09% | 17.11%
2 | 2026-07-20 | 2026-07-26 | A1.2, A1.3, A2.1 | A1.2: Model normal and abnormal operating scenarios A1.3: Define firmware, cloud, mobile, factory and recovery boundaries A2.1: Write uniquely identified functional requirements | A1.2: Normal/abnormal scenario catalogue A1.3: System context diagram and product-boundary document |  | 2.725%
3 | 2026-07-27 | 2026-08-02 | A2.1, A2.2, A2.3 | A2.1: Write uniquely identified functional requirements A2.2: Set measurable non-functional budgets for timing, memory, power, availability and security A2.3: Define hardware, communications, diagnostics, manufacturing and OTA interfaces plus environmental constraints | A2.1: System requirements specification with FR identifiers A2.2: Non-functional requirements specification |  | 4.36%
4 | 2026-08-03 | 2026-08-09 | A2.3, A2.4, A3.1 | A2.3: Define hardware, communications, diagnostics, manufacturing and OTA interfaces plus environmental constraints A2.4: Build requirements traceability matrix and initial acceptance-test list A3.1: Validate ESP32-S3/Heltec V3 hardware constraints, pins, flash, PSRAM, RF, USB and power controls | A2.3: Interface control document and environmental/regulatory checklist A2.4: Requirements traceability matrix and acceptance-test catalogue |  | 5.995%
5 | 2026-08-10 | 2026-08-16 | A3.1, A3.2 | A3.1: Validate ESP32-S3/Heltec V3 hardware constraints, pins, flash, PSRAM, RF, USB and power controls A3.2: Prototype high-risk software capabilities: provisioning, LoRaWAN, TLS, OTA, sleep and storage recovery | A3.1: Hardware feasibility report and verified pin/constraint list |  | 7.084%
6 | 2026-08-17 | 2026-08-23 | A3.2, A3.3 | A3.2: Prototype high-risk software capabilities: provisioning, LoRaWAN, TLS, OTA, sleep and storage recovery A3.3: Create risk register and preliminary threat model; close Cluster A gate | A3.2: Proof-of-concept applications and test logs A3.3: Risk register, threat model and requirements-baseline review record | G-A: Risks have mitigations and the requirements baseline is accepted | 8.283%
7 | 2026-08-24 | 2026-08-30 | B1.1, B1.2 | B1.1: Install and pin VS Code, ESP-IDF, Git, Python, CMake/Ninja, drivers and debugger support B1.2: Build, flash and monitor a minimal ESP32-S3 project from the controlled workspace | B1.1: Tool-version manifest and installation record |  | 9.373%
8 | 2026-08-31 | 2026-09-06 | B1.2, B1.3, B2.1 | B1.2: Build, flash and monitor a minimal ESP32-S3 project from the controlled workspace B1.3: Document workstation setup and onboarding checks B2.1: Create production repository structure, .gitignore and component directories | B1.2: Minimal project binary, flash log and serial monitor capture B1.3: Developer setup guide and onboarding checklist B2.1: Initialized repository and directory baseline |  | 11.01%
9 | 2026-09-07 | 2026-09-13 | B2.2, B2.3, B3.1 | B2.2: Define branching, review, commit, release-tag and semantic-version policies B2.3: Embed firmware metadata and verify secrets are excluded B3.1: Create debug, validation and production sdkconfig profiles | B2.2: Source-control and versioning policy B2.3: Build metadata output and secret-scan evidence |  | 12.64%
10 | 2026-09-14 | 2026-09-20 | B3.1, B3.2 | B3.1: Create debug, validation and production sdkconfig profiles B3.2: Implement bootstrap, build, flash, erase, monitor and release scripts | B3.1: Pinned sdkconfig defaults for all profiles |  | 13.73%
11 | 2026-09-21 | 2026-09-27 | B3.2, B3.3, B4.1 | B3.2: Implement bootstrap, build, flash, erase, monitor and release scripts B3.3: Add ESP-IDF version guard, image-size checks and deterministic build metadata B4.1: Create CI stages for format, static checks, host tests and profile builds | B3.2: PowerShell/Python build-tool scripts B3.3: Version-check and image-budget reports |  | 15.37%
12 | 2026-09-28 | 2026-10-04 | B4.1, B4.2, B4.3 | B4.1: Create CI stages for format, static checks, host tests and profile builds B4.2: Archive binaries, ELF, MAP, partition table, sdkconfig, logs and test reports B4.3: Reproduce clean checkout-to-flash workflow and close Cluster B gate | B4.1: CI workflow and successful pipeline run B4.2: CI artifact archive B4.3: Engineering-baseline gate review | G-B: Toolchain, repository, scripts and CI are reproducible | 17.11%
13 | 2026-10-05 | 2026-10-11 | C1.1, C1.2 | C1.1: Define firmware layers, component groups and dependency direction C1.2: Specify component APIs, ownership, threading, initialization and error contracts | C1.1: Architecture document and component diagram |  | 18.2%
14 | 2026-10-12 | 2026-10-18 | C1.2, C1.3 | C1.2: Specify component APIs, ownership, threading, initialization and error contracts C1.3: Record architecture decisions and review for circular/overlapping responsibilities | C1.2: Component interface specifications C1.3: Architecture decision records and review checklist |  | 19.29%
15 | 2026-10-19 | 2026-10-25 | C2.1, C2.2, C4.1 | C2.1: Define board pins, active levels, pulls, electrical capabilities and revision detection C2.2: Implement safe startup, peripheral power sequencing and bus initialization C4.1: Design 8 MB partition table and warning/release/hard image budgets | C2.1: Board pin map and revision strategy |  | 20.93%
16 | 2026-10-26 | 2026-11-01 | C2.2, C2.3, C4.1 | C2.2: Implement safe startup, peripheral power sequencing and bus initialization C2.3: Build board self-test for GPIO, buttons, LED, I2C, SPI, OLED, SX1262, ADC and Vext C4.1: Design 8 MB partition table and warning/release/hard image budgets | C2.2: Board initialization code and startup-sequence trace C4.1: Production partition CSV and size-budget rationale |  | 22.56%
17 | 2026-11-02 | 2026-11-08 | C2.3, C4.2 | C2.3: Build board self-test for GPIO, buttons, LED, I2C, SPI, OLED, SX1262, ADC and Vext C4.2: Define boot selection, trial-boot, rollback and recovery-entry flows | C2.3: Board self-test application and pass report C4.2: Boot-flow and recovery-flow diagrams |  | 23.65%
18 | 2026-11-09 | 2026-11-15 | C3.1, C4.3, C4.4 | C3.1: Implement HAL wrappers for GPIO, I2C, SPI, UART, ADC, PWM, timers and power C4.3: Implement recovery application skeleton and partition inspection C4.4: Validate partition offsets, maximum images and migration constraints | C4.3: Bootable recovery image C4.4: Partition validation report |  | 25.29%
19 | 2026-11-16 | 2026-11-22 | C3.1, C3.2 | C3.1: Implement HAL wrappers for GPIO, I2C, SPI, UART, ADC, PWM, timers and power C3.2: Implement core sensor, actuator, LED and button drivers with structured errors | C3.1: HAL components and API documentation |  | 26.38%
20 | 2026-11-23 | 2026-11-29 | C3.2, C3.3 | C3.2: Implement core sensor, actuator, LED and button drivers with structured errors C3.3: Implement OLED, SX1262 and battery-monitor drivers | C3.2: Core device-driver components and unit tests |  | 27.47%
21 | 2026-11-30 | 2026-12-06 | C3.3, C3.4 | C3.3: Implement OLED, SX1262 and battery-monitor drivers C3.4: Run bus recovery, repeated-init and ownership/concurrency tests | C3.3: Display, radio and battery driver test applications C3.4: Driver fault-injection report |  | 28.56%
22 | 2026-12-07 | 2026-12-13 | C5.1, C5.2, C6.1 | C5.1: Implement early startup, reset capture, NVS/config/identity load and board initialization C5.2: Implement startup state machine and service result model C6.1: Define RTOS task ownership, priorities, stack budgets and liveness conditions | C5.1: Minimal app_main and early-startup trace C6.1: Task architecture and priority/stack table |  | 30.19%
23 | 2026-12-14 | 2026-12-20 | C5.2, C5.3, C6.2 | C5.2: Implement startup state machine and service result model C5.3: Implement boot-loop persistence, safe mode and recovery escalation C6.2: Implement typed commands/events, bounded queues, notifications and timers | C5.2: Startup coordinator and supervisor |  | 31.83%
24 | 2026-12-21 | 2026-12-27 | C5.3, C5.4, C6.2, C6.3 | C5.3: Implement boot-loop persistence, safe mode and recovery escalation C5.4: Test normal, degraded, fatal and recovery startup paths C6.2: Implement typed commands/events, bounded queues, notifications and timers C6.3: Configure stack monitoring, watchdog participation and blocking-time limits | C5.3: Boot-failure policy and safe-mode implementation C5.4: Startup-path test report C6.2: Queue/event catalogue and messaging framework |  | 34.01%
25 | 2026-12-28 | 2027-01-03 | C6.3, C6.4 | C6.3: Configure stack monitoring, watchdog participation and blocking-time limits C6.4: Stress queues, notifications, ISR handoff and concurrent service ownership | C6.3: Runtime stack/watchdog metrics C6.4: RTOS concurrency test report |  | 35.1%
26 | 2027-01-04 | 2027-01-10 | C7.1, C7.2 | C7.1: Classify factory identity, user config, operational state and bulk data; define schemas C7.2: Implement configuration service with integrity and atomic activation | C7.1: Data classification and versioned schema specification |  | 36.19%
27 | 2027-01-11 | 2027-01-17 | C7.2, C7.3 | C7.2: Implement configuration service with integrity and atomic activation C7.3: Implement migrations, filesystem rotation, full-storage and cleanup behavior | C7.2: Configuration service and atomic-update tests |  | 37.28%
28 | 2027-01-18 | 2027-01-24 | C7.3, C7.4 | C7.3: Implement migrations, filesystem rotation, full-storage and cleanup behavior C7.4: Execute storage corruption and power-loss tests | C7.3: Migration functions and filesystem service C7.4: Storage power-loss and recovery report |  | 38.37%
29 | 2027-01-25 | 2027-01-31 | C8.1, C8.2 | C8.1: Implement structured logging and stable event-ID catalogue C8.2: Implement diagnostic snapshot for versions, reset, heap, stacks, network and storage | C8.1: Logging framework and event catalogue |  | 39.46%
30 | 2027-02-01 | 2027-02-07 | C8.2, C8.3 | C8.2: Implement diagnostic snapshot for versions, reset, heap, stacks, network and storage C8.3: Enable watchdog layers, core-dump partition and pre-crash event buffer | C8.2: Health-monitor service and snapshot output |  | 40.54%
31 | 2027-02-08 | 2027-02-14 | C8.3, C8.4 | C8.3: Enable watchdog layers, core-dump partition and pre-crash event buffer C8.4: Document core-dump retrieval and diagnostic triage workflow | C8.3: Watchdog/core-dump configuration and captured sample fault C8.4: Field diagnostic and core-dump guide |  | 41.63%
32 | 2027-02-15 | 2027-02-21 | C.G1 | C.G1: Integrate board, drivers, storage, startup, RTOS and diagnostics into platform baseline |  |  | 42.34%
33 | 2027-02-22 | 2027-02-28 | C.G1, C.G2 | C.G1: Integrate board, drivers, storage, startup, RTOS and diagnostics into platform baseline C.G2: Run 72-hour platform soak, close blockers and approve Cluster C gate | C.G1: Integrated platform build and interface test report | G-C: Platform services run together without product-specific coupling | 43.76%
34 | 2027-03-01 | 2027-03-07 | C.G2 | C.G2: Run 72-hour platform soak, close blockers and approve Cluster C gate | C.G2: Soak report, defect closure list and platform-baseline approval | G-C: No unexplained reset, heap drift or critical open defect remains | 44.47%
35 | 2027-03-08 | 2027-03-14 | D1.1, D8.1 | D1.1: Define device states, product commands and events D8.1: Finalize security architecture, assets, trust boundaries and attack surfaces | D1.1: Product state diagram and command/event catalogue |  | 45.56%
36 | 2027-03-15 | 2027-03-21 | D1.2, D8.1 | D1.2: Implement transition handlers, timeouts, failure paths and persistent state D8.1: Finalize security architecture, assets, trust boundaries and attack surfaces | D1.2: State transition table and implementation D8.1: Updated threat model and security architecture |  | 46.65%
37 | 2027-03-22 | 2027-03-28 | D1.3 | D1.3: Unit-test normal, degraded, maintenance, update, safe and recovery transitions | D1.3: State-machine unit-test report |  | 47.19%
38 | 2027-03-29 | 2027-04-04 | D2.1, D5.1 | D2.1: Implement single-owner Wi-Fi network manager and lifecycle states D5.1: Implement acquisition validation, calibration, normalization and filtering pipeline | D2.1: Network manager component |  | 48.28%
39 | 2027-04-05 | 2027-04-11 | D2.2, D5.1, D5.2 | D2.2: Implement selected provisioning and authorized reset workflow D5.1: Implement acquisition validation, calibration, normalization and filtering pipeline D5.2: Implement control rules, hysteresis, timing, safety limits and manual override | D2.2: Provisioning service and provisioning test logs D5.1: Acquisition service and sample-quality tests |  | 49.92%
40 | 2027-04-12 | 2027-04-18 | D2.3, D2.4, D5.2 | D2.3: Implement exponential backoff with jitter and connection diagnostics D2.4: Test long-duration network loss, recovery and repeated provisioning D5.2: Implement control rules, hysteresis, timing, safety limits and manual override | D2.3: Retry/backoff implementation and metrics D2.4: Connectivity resilience report D5.2: Control service and rule-test report |  | 51.55%
41 | 2027-04-19 | 2027-04-25 | D3.1, D5.3 | D3.1: Integrate SX1262 reset, busy, DIO, frequency, power, sleep and wake behavior D5.3: Implement calibration storage, validity, migration and corrupt-data fallback | D5.3: Calibration service and migration tests |  | 52.64%
42 | 2027-04-26 | 2027-05-02 | D3.1, D3.2, D5.4 | D3.1: Integrate SX1262 reset, busy, DIO, frequency, power, sleep and wake behavior D3.2: Integrate LoRaWAN OTAA join, uplink, downlink, ADR and retry scheduling D5.4: Verify control timing, boundaries and safe-output states | D3.1: Radio service and radio test logs D5.4: Algorithm, latency and safe-state test report |  | 54.28%
43 | 2027-05-03 | 2027-05-09 | D3.2, D3.3, D8.2 | D3.2: Integrate LoRaWAN OTAA join, uplink, downlink, ADR and retry scheduling D3.3: Persist frame counters and enforce region/key handling rules D8.2: Define per-device identity, key management, signing, eFuse and debug policies | D3.2: LoRaWAN manager and network-server test evidence |  | 55.91%
44 | 2027-05-10 | 2027-05-16 | D3.3, D3.4, D8.2 | D3.3: Persist frame counters and enforce region/key handling rules D3.4: Run long-duration join/uplink/downlink stability test D8.2: Define per-device identity, key management, signing, eFuse and debug policies | D3.3: Counter persistence and regional compliance tests D3.4: LoRaWAN endurance report D8.2: Key-management procedure and eFuse/debug plan |  | 57.55%
45 | 2027-05-17 | 2027-05-23 | D4.1 | D4.1: Define transport abstraction and versioned telemetry schema | D4.1: Transport API and telemetry specification |  | 58.09%
46 | 2027-05-24 | 2027-05-30 | D4.2, D4.3 | D4.2: Implement cloud client, certificate validation and response handling D4.3: Implement bounded offline spool, retry, expiry and deduplication | D4.2: Cloud client and integration logs |  | 59.18%
47 | 2027-05-31 | 2027-06-06 | D4.3, D4.4 | D4.3: Implement bounded offline spool, retry, expiry and deduplication D4.4: Test disconnects, invalid payloads, backlog replay and throttling | D4.3: Offline queue and backlog test evidence D4.4: Cloud outage and replay report |  | 60.27%
48 | 2027-06-07 | 2027-06-13 | D6.1 | D6.1: Define active, idle, sleep, charging and battery-critical states | D6.1: Power-state model |  | 60.82%
49 | 2027-06-14 | 2027-06-20 | D6.2 | D6.2: Implement sleep coordinator, state save, peripheral shutdown and wake handling | D6.2: Sleep/wake implementation and traces |  | 61.36%
50 | 2027-06-21 | 2027-06-27 | D6.3, D6.4 | D6.3: Measure boot, active, Wi-Fi, LoRa, idle and sleep currents; estimate battery life D6.4: Run repeated sleep/wake and low-battery behavior tests | D6.3: Power-consumption report and battery-life estimate D6.4: Power-cycle repeatability report |  | 62.45%
51 | 2027-06-28 | 2027-07-04 | D7.1, D7.2 | D7.1: Define signed OTA manifest, compatibility and secure-version policy D7.2: Implement manifest fetch, download, cryptographic verification and staging | D7.1: OTA manifest specification |  | 63.54%
52 | 2027-07-05 | 2027-07-11 | D7.2 | D7.2: Implement manifest fetch, download, cryptographic verification and staging | D7.2: OTA client and verifier tests |  | 64.09%
53 | 2027-07-12 | 2027-07-18 | D7.3, D8.3 | D7.3: Implement trial-boot acceptance, rollback and boot-loop interaction D8.3: Integrate secure boot, flash/NVS encryption, TLS validation and log redaction on validation hardware | D7.3: Trial-boot and rollback evidence |  | 65.18%
54 | 2027-07-19 | 2027-07-25 | D7.4, D8.3, D8.4 | D7.4: Complete recovery installer and test power loss during OTA paths D8.3: Integrate secure boot, flash/NVS encryption, TLS validation and log redaction on validation hardware D8.4: Implement security failure handling and verify unauthorized workflows fail | D7.4: Recovery application and OTA power-loss matrix D8.3: Security-validation build and configuration evidence D8.4: Security failure-path test report |  | 66.81%
55 | 2027-07-26 | 2027-08-01 | D.G1 | D.G1: Integrate product state, connectivity, LoRaWAN, cloud, sensing, power, OTA and security | D.G1: Feature-complete integrated build and system smoke report | G-D: All mandatory features operate together | 67.57%
56 | 2027-08-02 | 2027-08-08 | D.G2 | D.G2: Close feature blockers and approve Cluster D gate | D.G2: Feature-complete gate review and defect disposition | G-D: No critical feature remains prototype-only | 68.34%
57 | 2027-08-09 | 2027-08-15 | E1.1, E2.1 | E1.1: Enforce warning policy, formatting, naming, headers and API documentation E2.1: Expand host tests for state machines, parsers, serialization, migration, retry and algorithms | E1.1: Compiler/style report |  | 69.43%
58 | 2027-08-16 | 2027-08-22 | E1.2, E1.3, E2.1 | E1.2: Run static analysis for memory, integer, locking, resource and return-value defects E1.3: Review complexity, dead code, duplicate code and approved deviations E2.1: Expand host tests for state machines, parsers, serialization, migration, retry and algorithms | E1.2: Static-analysis report E1.3: Code-review record and deviation register E2.1: Host unit-test suite and report |  | 71.06%
59 | 2027-08-23 | 2027-08-29 | E2.2 | E2.2: Run target unit tests for storage, drivers, queues, timers, network and OTA managers | E2.2: Target component-test report |  | 71.61%
60 | 2027-08-30 | 2027-09-05 | E2.3 | E2.3: Complete mocks/fakes, practical coverage review and CI automation | E2.3: Test doubles, coverage summary and automated test job |  | 72.15%
61 | 2027-09-06 | 2027-09-12 | E3.1 | E3.1: Test startup/storage, driver/acquisition, event/state, network/cloud and OTA/supervisor integration | E3.1: Platform integration-test report |  | 72.7%
62 | 2027-09-13 | 2027-09-19 | E3.2, E3.3 | E3.2: Inject bus timeout, disconnect, invalid message, storage full, corruption and missing peripheral E3.3: Update requirement-to-test traceability and defect records | E3.2: Interface-failure test results E3.3: Updated RTM and defect list |  | 73.79%
63 | 2027-09-20 | 2027-09-26 | E4.1 | E4.1: Build HIL control for power, reset, GPIO, serial logs and network interruption | E4.1: HIL framework and automation scripts |  | 74.33%
64 | 2027-09-27 | 2027-10-03 | E4.2 | E4.2: Run factory reset-to-provisioning-to-operation-to-OTA end-to-end scenarios | E4.2: End-to-end system-test report |  | 74.88%
65 | 2027-10-04 | 2027-10-10 | E4.3, E5.1 | E4.3: Run 24-hour smoke, multi-day stability, reboot, provisioning, sleep and backlog tests E5.1: Interrupt power during storage writes, migration, OTA switch, trial boot and provisioning | E4.3: Long-duration report and stability metrics E5.1: Power-loss test report |  | 75.97%
66 | 2027-10-11 | 2027-10-17 | E5.2 | E5.2: Inject network, DNS, TLS, authentication, LoRaWAN and cloud server failures | E5.2: Communication fault-injection report |  | 76.51%
67 | 2027-10-18 | 2027-10-24 | E5.3 | E5.3: Test low/fragmented heap, full queues/filesystem, rapid events, task stalls and deadlocks | E5.3: Resource/watchdog fault report |  | 77.06%
68 | 2027-10-25 | 2027-10-31 | E6.1, E6.2 | E6.1: Measure heap, fragmentation, internal/DMA memory, stacks, CPU load and idle margin E6.2: Verify image sizes, filesystem reserve, boot/join/control/OTA/recovery timing | E6.1: Memory and CPU qualification report E6.2: Flash and timing qualification report |  | 78.15%
69 | 2027-11-01 | 2027-11-07 | E7.1, E7.2 | E7.1: Verify unsigned/modified/wrong-product/wrong-hardware/old-version image rejection and rollback E7.2: Verify certificates, hostname, auth failures, debug restrictions and recovery authorization | E7.1: Firmware and storage security-validation report E7.2: Communication/interface security report |  | 79.24%
70 | 2027-11-08 | 2027-11-14 | E.G1 | E.G1: Close critical/high defects, freeze release candidate and approve Cluster E gate | E.G1: Release-candidate approval, reproducible build and residual-risk record | G-E: All requirements have evidence and critical/high defects are closed or accepted | 80.05%
71 | 2027-11-15 | 2027-11-21 | F1.1 | F1.1: Implement manufacturing firmware covering flash, RAM, GPIO, UI, buses, radio, wireless, ADC and identity | F1.1: Manufacturing-test application and coverage matrix |  | 80.6%
72 | 2027-11-22 | 2027-11-28 | F1.2 | F1.2: Develop station software, fixture control, programming and result capture | F1.2: Manufacturing station software and fixture test |  | 81.14%
73 | 2027-11-29 | 2027-12-05 | F1.3, F2.1 | F1.3: Define traceability record, retest, repair and fail containment F2.1: Implement controlled identity, certificate and security provisioning sequence | F1.3: Manufacturing record schema and retest procedure F2.1: Provisioning workflow and audit record |  | 82.23%
74 | 2027-12-06 | 2027-12-12 | F2.2, F2.3 | F2.2: Implement eFuse programming with preconditions, readback and failure recovery F2.3: Reboot and verify secure boot, flash encryption and final production state | F2.2: eFuse script and irreversible-operation checklist F2.3: Post-provisioning security-state report |  | 83.32%
75 | 2027-12-13 | 2027-12-19 | F3.1, F3.2 | F3.1: Package application, recovery, bootloader, partitions, OTA/factory images, ELF, MAP and checksums F3.2: Create manifest, SBOM, release notes, dependency lock and retention archive | F3.1: Signed release package F3.2: Release manifest, SBOM, notes and archived symbols |  | 84.41%
76 | 2027-12-20 | 2027-12-26 | F4.1 | F4.1: Run pilot batch using final board, fixture, provisioning, security and package process | F4.1: Pilot production report |  | 84.96%
77 | 2027-12-27 | 2028-01-02 | F4.2 | F4.2: Monitor yield, RF, boot, OTA, battery, reset and cloud behavior | F4.2: Yield and field-trial metrics |  | 85.5%
78 | 2028-01-03 | 2028-01-09 | F4.3, F.G1 | F4.3: Conduct go/no-go review for defects, yield, security, rollback and support readiness F.G1: Tag and release production firmware; archive complete evidence package | F4.3: Production-release approval record F.G1: Production tag, signed artifacts and permanent evidence archive | G-F: Manufacturing, support and rollback readiness are accepted G-F: Approved production release is reproducible and recoverable | 87.14%
79 | 2028-01-10 | 2028-01-16 | G1.1, G2.1, G3.1 | G1.1: Deploy health dashboard for versions, resets, boot loops, OTA, connectivity, heap, storage and watchdogs G2.1: Define severity, incident intake, triage, core-dump and root-cause workflow G3.1: Roll out to internal and engineering fleets; monitor stop criteria | G1.1: Device-health dashboard and metric definitions G2.1: Incident-management procedure and templates G3.1: Internal rollout report |  | 88.77%
80 | 2028-01-17 | 2028-01-23 | G1.2, G2.2, G3.2 | G1.2: Set alert thresholds and publish support diagnostic procedure G2.2: Rehearse hotfix, regression, rollback and controlled release workflow G3.2: Roll out to pilot customers and small production percentage | G1.2: Alert rules and support guide |  | 90.41%
81 | 2028-01-24 | 2028-01-30 | G2.2, G3.2 | G2.2: Rehearse hotfix, regression, rollback and controlled release workflow G3.2: Roll out to pilot customers and small production percentage | G2.2: Hotfix rehearsal report G3.2: Pilot rollout dashboard and decision record |  | 91.5%
82 | 2028-01-31 | 2028-02-06 | G2.3, G3.3 | G2.3: Operate incident review and corrective-action loop during stabilization G3.3: Expand staged rollout to larger percentages and full fleet |  |  | 92.43%
83 | 2028-02-07 | 2028-02-13 | G2.3, G3.3 | G2.3: Operate incident review and corrective-action loop during stabilization G3.3: Expand staged rollout to larger percentages and full fleet |  |  | 93.35%
84 | 2028-02-14 | 2028-02-20 | G2.3, G3.3 | G2.3: Operate incident review and corrective-action loop during stabilization G3.3: Expand staged rollout to larger percentages and full fleet | G3.3: Full rollout report |  | 94.28%
85 | 2028-02-21 | 2028-02-27 | G2.3, G4.1 | G2.3: Operate incident review and corrective-action loop during stabilization G4.1: Assess framework/dependency security fixes, support dates, APIs, bootloader, size and radio impact | G4.1: Upgrade-impact report |  | 95.2%
86 | 2028-02-28 | 2028-03-05 | G2.3, G4.2 | G2.3: Operate incident review and corrective-action loop during stabilization G4.2: Run clean build, storage, OTA, rollback, power-loss, security, performance and endurance regression | G4.2: Dependency-upgrade regression report |  | 96.13%
87 | 2028-03-06 | 2028-03-12 | G2.3, G5.1 | G2.3: Operate incident review and corrective-action loop during stabilization G5.1: Define hardware compatibility matrix and update board revision detection/BSP | G5.1: Hardware compatibility matrix and BSP update |  | 97.06%
88 | 2028-03-13 | 2028-03-19 | G2.3, G5.2 | G2.3: Operate incident review and corrective-action loop during stabilization G5.2: Test peripherals, boot, RF and OTA across supported revisions; reject incompatible images | G5.2: Hardware-revision qualification report |  | 97.98%
89 | 2028-03-20 | 2028-03-26 | G2.3, G6.1 | G2.3: Operate incident review and corrective-action loop during stabilization G6.1: Define final firmware, signing-key, cloud shutdown, credential revocation and retention policy | G6.1: End-of-life policy |  | 98.91%
90 | 2028-03-27 | 2028-04-02 | G2.3, G6.2 | G2.3: Operate incident review and corrective-action loop during stabilization G6.2: Archive final firmware/tools/records and complete product-closure review | G2.3: Incident log, RCA and corrective-action records G6.2: Product-closure package and approval | G-G: Final artifacts and responsibilities are formally closed | 100%

## Source & Guidance
Source Mapping and Workbook Guidance
Item | Detail
Source | Uploaded ESP32-S3 Production Firmware Development Lifecycle markdown
Lifecycle hierarchy | Program → Cluster → Phase → Sub-phase → Work package → Deliverable → Exit gate
Owner model | Every task is assigned to Me; no additional resource assumptions
Schedule baseline | Week 1 starts 2026-07-13; production release Week 78; lifecycle baseline ends Week 90
Progress basis | Actual Completion is evidence-based and initialized at 0%
Weighting | Task weight is normalized from duration × complexity (Effort Points)
Dependency notation | Comma-separated predecessor WBS IDs; primarily finish-to-start
Gate Summary
Gate | Week | Required Result | Evidence Row
G-A | 6 | Approved requirements and feasibility | A3.3
G-B | 12 | Reproducible toolchain, repository and CI | B4.3
G-C | 34 | Stable reusable platform baseline | C.G2
G-D | 56 | Complete integrated product features | D.G2
G-E | 70 | Qualified release candidate | E.G1
G-F | 78 | Controlled production release | F4.3 / F.G1
G-G | 90 | Managed lifecycle and closure baseline | G6.2
Definition of Done Applied to Every Work Package
1 | Requirements/design are identified and documented.
2 | Interfaces, ownership and error behavior are explicit.
3 | Implementation is reviewed and CI passes.
4 | Normal, boundary and failure behavior are tested.
5 | Resource and security impact are reviewed.
6 | Evidence is linked or stored and no critical defect remains.